# INCIDENT REPORT — INC0001234

Incident ID: INC0001234

Priority: P1 — Critical

Status: Resolved

Opened: 2025-01-14  03:47 UTC

Resolved: 2025-01-14  06:22 UTC

Duration: 2 hours 35 minutes  (SLA target: 2 hours — BREACH by 35 min)

Affected Users: 847 (APAC region — Singapore, Sydney, Tokyo)

Business Impact: USD 142,000 (SAP EDI: $94K, staff productivity: $48K, SLA credits: $12K)

Incident Manager: James Wu (CTO)

Technical Lead: Mike Torres (Senior Network Architect)

# 1. Executive Summary

A Priority 1 BGP routing outage affecting all APAC network connections began at 03:47 UTC on 14 January 2025. The outage was caused by an Ansible Tower automation job (AT-4421) that incorrectly applied a Disaster Recovery BGP community filter to production routers. The job bypassed the Network Change Advisory Board approval gate due to a defect in the CI/CD pipeline approval logic. Three APAC core routers (APAC-CORE-R1, R2, and R3) lost all six BGP peer sessions simultaneously. 847 users across Singapore, Sydney, and Tokyo were unable to access corporate systems including SAP ERP, ServiceNow, and Salesforce CRM for the duration. The incident was resolved by rolling back the Ansible job and restoring BGP configuration at 06:22 UTC, 2 hours 35 minutes after initial impact.

# 2. Incident Timeline

| Time (UTC) | Event | Action Taken | By Whom |
| --- | --- | --- | --- |
| 03:47 | BGP peer loss detected — APAC-CORE-R1 alert fired in Datadog | NOC acknowledges P1 alert | NOC L1 — Priya Sharma |
| 03:49 | Confirmed P1 — all 6 BGP peers on R1 showing 'Idle' state | Incident bridge opened: #inc-1234 in Slack | NOC L1 — Priya Sharma |
| 03:52 | APAC-CORE-R2 and R3 also lose all BGP peers — full APAC outage confirmed | Incident Commander declared — James Wu paged | NOC L2 — David Park |
| 03:55 | Mike Torres joins bridge — begins BGP configuration review | Ansible Tower job log review begins | Mike Torres |
| 04:08 | Root cause identified: AT-4421 applied DR BGP community filter to production | Approval gate defect confirmed in Jenkinsfile | Mike Torres + DevOps |
| 04:15 | Change Board emergency approval obtained for rollback | Emergency CAB approval via phone bridge | James Wu |
| 04:22 | Rollback script executed on APAC-CORE-R1 — BGP config restored | BGP peers begin re-establishing | Mike Torres |
| 05:48 | APAC-CORE-R1 BGP fully converged — R2 and R3 restoration in progress | User communications sent — ETA 30 minutes | Comms team |
| 06:22 | All APAC BGP peers restored — full connectivity confirmed | Incident resolved, users notified | Mike Torres |
| 06:45 | Post-mortem scheduled for 2025-01-16 10:00 UTC | All corrective actions logged in ServiceNow | James Wu |

# 3. Root Cause Analysis

## 3.1 Technical Root Cause

Ansible Tower automation job AT-4421 was designed to apply Disaster Recovery BGP policies to DR-environment routers only. The CI/CD pipeline approval gate in Jenkinsfile evaluated the condition 'state != Cancelled' rather than 'state == Approved', meaning any job that had not been explicitly cancelled would pass the gate — including unapproved jobs targeting production infrastructure. This allowed AT-4421 to execute against APAC production routers (APAC-CORE-R1, R2, R3) without Network CAB review. The DR BGP community filter overwrote production BGP policy, causing all six peer sessions to be withdrawn simultaneously.

## 3.2 Contributing Factors

| Factor | Description | Control Gap |
| --- | --- | --- |
| CI/CD approval gate defect | Jenkinsfile gate evaluated state != Cancelled instead of state == Approved — passed all non-cancelled jobs | Code review did not catch the logic inversion — boolean logic tested only happy path |
| Router inventory tagging | AT-4421 targeted routers tagged 'APAC' — both DR and production APAC routers share this tag | DR and production environments use overlapping Ansible inventory tags — no environment segregation |
| Pre-flight validation absent | No mechanism to diff intended BGP config change against current production state before executing | Ansible playbook did not include a dry-run or pre-flight validation step |
| Change Board bypass | Emergency changes require CAB review, but AT-4421 was classified as automated routine, not a change | Automated jobs touching network configuration not classified as changes requiring CAB approval |

# 4. Business Impact

| Impact Category | Systems / Services Affected | Duration | Financial Cost |
| --- | --- | --- | --- |
| SAP ERP — EDI Transactions | All APAC SAP application servers — EDI interface to logistics partners | 2 hr 35 min | USD 94,000 |
| Staff Productivity | 847 APAC users unable to access corporate applications | 2 hr 35 min | USD 48,000 |
| Customer SLA Credits | 3 enterprise customers in SG/AU triggered SLA breach credits | N/A — credit applied | USD 12,000 |
| Salesforce CRM Access | Sales team unable to update opportunities during APAC business hours | 2 hr 35 min | USD 28,000 |
| Incident Response Overtime | NOC, Network, and DevOps teams — after-hours response | N/A | USD 2,040 |
| TOTAL |  |  | USD 142,000 |

# 5. Corrective Actions

| ID | Action | Owner | Due Date | Status |
| --- | --- | --- | --- | --- |
| CA-01 | Fix Jenkinsfile approval gate: change condition from state != Cancelled to state == Approved with explicit Allow-list of permitted states | Platform Engineering | 2025-01-21 | In Progress |
| CA-02 | Add pre-flight diff check to Ansible playbooks affecting network devices — abort if diff exceeds 5-line threshold | Automation Team | 2025-01-28 | In Progress |
| CA-03 | Separate DR and production Ansible inventory by environment prefix — never share APAC tag across both | Mike Torres | 2025-01-24 | Complete |
| CA-04 | Add change classification for all automated jobs touching Tier 1 network devices — require CAB approval | Change Manager | 2025-01-21 | Complete |
| CA-05 | Update Ansible Tower runbook: add mandatory peer count validation step before executing BGP config changes | Sarah Chen | 2025-01-24 | Pending |
| CA-06 | Audit all 47 existing Ansible templates for incorrect approval gate logic — auto-scan with regex check | Automation Team | 2025-02-07 | Pending |
| CA-07 | Full post-mortem with all stakeholders including CTO and Head of Infrastructure | James Wu | 2025-01-21 | Scheduled |

# 6. SLA Assessment

This incident constitutes a P1 SLA breach. The contracted resolution time for Priority 1 incidents is 2 hours from time of detection. The actual resolution time was 2 hours 35 minutes — 35 minutes over the contractual SLA. Three enterprise customers have automatic SLA credit triggers for P1 breaches: Acme Global, Pacific Logistics, and SG Financial Services. Combined credit exposure is USD 12,000. The SLA compliance team will process these credits within 5 business days. The Q1 P1 SLA compliance rate is now 84.2% against the 99.0% target.